## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | Smart Saving |  |  |  |  | COMPANY NAME | [8 empty] | Imagine coperation
PROJECT MANAGER |  | Sasipa Wangkaew |  |  |  |  | DATE | [8 empty] | 2017-04-20
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX | [14 empty] | PHASE SEVEN | [14 empty] | PHASE EIGHT | [14 empty] | PHASE NINE | [14 empty] | PHASE TEN | [14 empty] | PHASE ELEVEN | [14 empty] | PHASE TWELVE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26 |  |  |  |  | WEEK 27 |  |  |  |  | WEEK 28 |  |  |  |  | WEEK 29 |  |  |  |  | WEEK 30 |  |  |  |  | WEEK 31 |  |  |  |  | WEEK 32 |  |  |  |  | WEEK 33 |  |  |  |  | WEEK 34 |  |  |  |  | WEEK 35 |  |  |  |  | WEEK 36
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Sasipa WangKaew | 2017-04-24 | 2017-04-27 | 4 | 0% | bar: WEEK 1 M to WEEK 1 R
1.1.1 | Project Charter Revisions | Sasipa WangKaew | 2017-04-28 | 2017-05-01 | 2 | 0% | bar: WEEK 1 F to WEEK 2 M; WEEK 2 W to WEEK 2 F
1.2 | Research | Dirk Eufinger | 2017-05-02 | 2017-05-09 | 6 | 0% | bar: WEEK 2 T to WEEK 3 T
1.3 | Projections | Rachaneewan Kachinrot | 2017-05-10 | 2017-05-18 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 W to WEEK 4 R
1.4 | Stakeholders | Rachaneewan Kachinrot | 2017-05-19 | 2017-05-29 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 6 M
1.5 | Guidelines | Piyaboot Jaroenpong | 2017-05-30 | 2017-06-07 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 6 T to WEEK 7 W
1.6 | Project Initiation | Piyaboot Jaroenpong | 2017-06-08 | 2017-06-08 | 1 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 7 R
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Sasipa WangKaew | 2017-06-09 | 2017-06-15 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 7 F to WEEK 8 R
2.2 | Budget | Rachaneewan Kachinrot | 2017-06-16 | 2017-06-22 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 8 F to WEEK 9 R
2.3 | Communication Plan | Dirk Eufinger | 2017-06-23 | 2017-06-29 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 9 F to WEEK 10 R
2.4 | Risk Management | Piyaboot Jaroenpong | 2017-06-30 | 2017-07-10 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 10 F to WEEK 12 M
3 | Project Launch & Execution
3.1 | Status & Tracking | Rachaneewan Kachinrot | 2017-07-11 | 2017-07-31 | 15 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 12 T to WEEK 15 M
3.2 | KPIs | Chris John | 2017-08-01 | 2017-08-24 | 15 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 15 T to WEEK 18 M
3.2.1 | Monitoring | Piyaboot Jaroenpong | 2017-08-25 | 2017-10-05 | 30 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 18 T to WEEK 24 M
3.2.2 | Forecasts | Piyaboot Jaroenpong | 2017-10-06 | 2017-10-19 | 10 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 24 T to WEEK 26 F
3.3 | Project Updates | Sambubi Eufinger | 2017-10-20 | 2017-10-26 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 26 M to WEEK 27 M
3.3.1 | Chart Updates | Piyaboot Jaroenpong | 2017-10-27 | 2017-11-02 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 27 T to WEEK 28 M
4 | Project Performance / Monitoring
4.1 | Project Objectives | Sasipa WangKaew | 2017-11-03 | 2017-11-30 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 28 T to WEEK 29 F
4.2 | Quality Deliverables | Rachaneewan Kachinrot | 2017-11-29 | 2017-11-13 | 7 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 29 M to WEEK 30 F
4.3 | Effort & Cost Tracking | Piyaboot Jaroenpong | 2017-11-14 | 2017-11-20 | 5 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 31 M to WEEK 32 F
4.4 | Project Performance | Bobcats Eufinger | 2017-11-21 | 2017-12-08 | 14 | 0% | bar: WEEK 2 W to WEEK 2 F; WEEK 32 M to WEEK 34 R
CLICK HERE TO CREATE WBS TEMPLATES WITH GANTT CHART IN SMARTSHEET

## WBS with Gantt Chart BLANK (hidden)
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 20%
100%
90%
40%
70%
60%
50%
100%
30%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET